## Planning
- |  | Game: | The worst knight in the kingdom
|  | Team Members: | Katarzyna Drobniewicz
Marta Stąporek
Sebastian Haliński
| Task category | Task name | Task description | Difficulty level [1-3] | Assigned to | Progress [none ¦ in progress ¦ done] | End date
1 | Must have | Story | Introduction screen (also about autors), a character creation screen, how to play. | 1 | Marta | in progress
2 |  | Movement | Moving character with WSAD | 3 | Sebastian | none
3 |  | Features | Diffrent look, printing life, points, time. Points and lifes printed on every level. | 3 | Kasia (lifes, time). Sebastian (points). | none
4 |  | 1 game levels | Questions. | 2 | Kasia | none
5 |  | 2 game level | Collecting items | 2 | Sebastian. | none
6
1 | Should have | Extra features on level | Colors, obstracles: river, bridge etc. | 2 | Marta | none
2 |  | Boss | Opponent in the game | 3 | Sebastian | none
3 |  | Fighting | Shooting | 2 | Marta | none
4
5
6
1 | Nice to have | ASCI art |  | 3 | Marta | none
2
3
4
5
6